## Project Summary
Project Summary
Project Name | Book Lovers
Project Manager | Võ Thanh Hiệp
Start date | 2023-10-07
Finish date | 2023-12-23
Days | Pro
Progress | 29.8%
Work hours | Pro
Remaining work hours | Pro
Remaining work days | Pro
Remaining weeks | Pro
Cost | Pro

## Task Schedule
[5 empty] | October 2023 | [29 empty] | November 2023 | [29 empty] | December 2023
WBS | Task description | Start date | Finish date | Progress | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
wbs | task | start | finish | progress | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | #
1 | Inception | 2023-10-07 | 2023-11-02 | 100% | [5 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
1.1 | Inception PA0 | 2023-10-07 | 2023-10-16 | 100% | [5 empty] | = | = | = | = | = | = | = | = | = | = | [15 empty] | ¦
1.1.1 | Choose role | 2023-10-07 | 2023-10-08 | 100% | [5 empty] | = | = | [23 empty] | ¦
1.1.2 | Create an environment to store project information | 2023-10-08 | 2023-10-09 | 100% | [6 empty] | = | = | [22 empty] | ¦
1.1.3 | Sprint plannig | 2023-10-10 | 2023-10-12 | 100% | [8 empty] | = | = | = | [19 empty] | ¦
1.1.4 | Weekly scrum | 2023-10-13 | 2023-10-16 | 100% | [11 empty] | = | = | = | = | [15 empty] | ¦
1.2 | Inception PA1 | 2023-10-17 | 2023-11-02 | 100% | [15 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
1.2.1 | Review Vision document and project plan | 2023-10-17 | 2023-10-18 | 100% | [15 empty] | = | = | [13 empty] | ¦
1.2.2 | Vision Document | 2023-10-19 | 2023-10-21 | 100% | [17 empty] | = | = | = | [10 empty] | ¦
1.2.3 | Risk management | 2023-10-22 | 2023-10-24 | 100% | [20 empty] | = | = | = | [7 empty] | ¦
1.2.4 | Project plan | 2023-10-25 | 2023-10-29 | 100% | [23 empty] | = | = | = | = | = |  |  | ¦
1.2.5 | Sprint Review and planning | 2023-10-30 | 2023-11-01 | 100% | [28 empty] | = | = | =
1.2.6 | Weekly scrum | 2023-11-01 | 2023-11-02 | 100% | [30 empty] | = | =
2 | Elaboration | 2023-11-03 | 2023-11-30 | 3.684% | [30 empty] | ¦ |  | =
2.1 | Elaboration PA2 | 2023-11-03 | 2023-11-16 | 7.778% | [30 empty] | ¦ |  | =
2.1.1 | Draw Use-case Diagram | 2023-11-03 | 2023-11-04 | 70% | [30 empty] | ¦ |  | =
2.1.2 | Write Use-case Specification | 2023-11-04 | 2023-11-05 | 0% | [30 empty] | ¦
2.1.3 | Revise the Project Plan | 2023-11-05 | 2023-11-06 | 0% | [30 empty] | ¦
2.1.4 | Revise the Vision document | 2023-11-06 | 2023-11-07 | 0% | [30 empty] | ¦
2.1.5 | Project plan | 2023-11-08 | 2023-11-12 | 0% | [30 empty] | ¦
2.1.6 | Sprint Review and planning | 2023-11-13 | 2023-11-15 | 0% | [30 empty] | ¦
2.1.7 | Weekly scrum | 2023-11-15 | 2023-11-16 | 0% | [30 empty] | ¦
2.2 | Elaboration PA3 | 2023-11-17 | 2023-11-30 | 0% | [30 empty] | ¦
2.2.1 | Draw the class diagram | 2023-11-17 | 2023-11-19 | 0% | [30 empty] | ¦
2.2.2 | Design the database | 2023-11-17 | 2023-11-19 | 0% | [30 empty] | ¦
2.2.3 | Design the draft version of the Architecture of the software | 2023-11-19 | 2023-11-21 | 0% | [30 empty] | ¦
2.2.4 | Update use-case specification document | 2023-11-21 | 2023-11-22 | 0% | [30 empty] | ¦
2.2.5 | Project plan | 2023-11-23 | 2023-11-25 | 0% | [30 empty] | ¦
2.2.6 | Sprint Review and planning | 2023-11-26 | 2023-11-29 | 0% | [30 empty] | ¦
2.2.7 | Weekly scrum | 2023-11-29 | 2023-11-30 | 0% | [30 empty] | ¦
3 | Construction | 2023-12-01 | 2023-12-23 | 0% | [30 empty] | ¦
3.1 | Construction PA4 | 2023-12-01 | 2023-12-14 | 0% | [30 empty] | ¦
3.1.1 | Revise SAD | 2023-12-01 | 2023-12-04 | 0% | [30 empty] | ¦
3.1.2 | Implement other core features | 2023-12-01 | 2023-12-04 | 0% | [30 empty] | ¦
3.1.3 | Implement the user interface for core features | 2023-12-01 | 2023-12-04 | 0% | [30 empty] | ¦
3.1.4 | Design test case | 2023-12-05 | 2023-12-06 | 0% | [30 empty] | ¦
3.1.5 | Project plan | 2023-12-07 | 2023-12-11 | 0% | [30 empty] | ¦
3.1.6 | Sprint Review and planning | 2023-12-11 | 2023-12-13 | 0% | [30 empty] | ¦
3.1.7 | Weekly scrum | 2023-12-13 | 2023-12-14 | 0% | [30 empty] | ¦
3.2 | Construction PA5 | 2023-12-15 | 2023-12-23 | 0% | [30 empty] | ¦
3.2.1 | Update test case | 2023-12-15 | 2023-12-15 | 0% | [30 empty] | ¦
3.2.2 | Test plan | 2023-12-15 | 2023-12-18 | 0% | [30 empty] | ¦
3.2.3 | Presentation Document | 2023-12-19 | 2023-12-21 | 0% | [30 empty] | ¦
3.2.4 | Demo video | 2023-12-21 | 2023-12-23 | 0% | [30 empty] | ¦

## TRANSGOOGLE (hidden)
translate (contact in English please) | dịch (vui lòng liên hệ bằng tiếng Anh)